## Sheet1
Milestone Review
Milestone | Date Expected | Date Completed | Notes
Project Proposal | 2021-02-05 | 2021-02-05
Design Review Mtg | 2021-03-31 | 2021-03-29
Tool Selection Review | 2021-03-31 | 2021-03-29
SPMP | 2021-04-10 | 2021-04-24 | I had to update my SPMP because I have changed few things on the project.
Github Repo Setup | 2021-03-23 | 2021-03-23
Website creation | 2021-03-23 | 2021-03-23
fetch API (Edamam) | 2021-04-01 | 2021-04-10 | Fetch functionality took me couple a days to figure out
CSS/bootstrap plugins | 2021-04-12 | 2021-04-12
Recipe Component | 2021-04-16 | 2021-04-15
Recipe Search Component | 2021-04-16 | 2021-04-16
Testing | 2021-04-18 | 2021-04-18
Pushed to deployment | 2021-04-21 | 2021-04-24 | I had an issue deploying on netlify and it will take me couple of days to figure out the reason.
Code Review | 2021-04-26 | 2021-04-24
Final Testing | 2021-04-28 | 2021-04-24
Push to Production | 2021-04-30 | 2021-04-24
Project Completion | 2021-04-30 | 2021-04-24
Project Presentation | 2021-05-11 | TBA